## Sheet1
BrainPower - AES - Gantt Chart
Tasks | Start Date | Duration | Completion Date
Feature prototoype - OCR | 2026-06-22 | 5 | 2026-06-26
Finalise Preliminary Report | 2026-06-27 | 1 | 2026-06-27
Video Presentation: Feature Prototype | 2026-06-28 | 1 | 2026-06-28
Distribution of Permission Letters | 2026-06-30 | 4 | 2026-07-05
Data Collection from Sample | 2026-07-01 | 14 | 2026-07-12
Testing - ASR Model | 2026-07-05 | 7 | 2026-07-12
Testing - Transformer Model | 2026-07-06 | 8 | 2026-07-13
User Interface Design | 2026-07-06 | 5 | 2026-07-13
Testing - Integrated System | 2026-07-13 | 6 | 2026-07-18
User Testing | 2026-07-20 | 12 | 2026-07-31
Draft Report | 2026-08-01 | 17 | 2026-08-17
Final Report | 2026-09-01 | 28 | 2026-09-28
Formulas:
Completion Date = [Start Date]+ [Duration] -1